## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Rahul | 2026-03-10 | Agent fails when chaining multiple tools. Expected smooth execution, actual error thrown | Sprint 1 | Priya | Functional | Fixed tool chaining logic in LangChain | 2026-03-11 | Closed | Tested successfully
2 | Aman | 2026-03-11 | Response time too high for multi-agent tasks | Sprint 1 | Rahul | Performance | Optimized prompt handling | - | Open | Needs more tuning
3 | Priya | 2026-03-12 | UI not showing agent output correctly | Sprint 2 | Aman | UI | Fixed frontend rendering issue | 2026-03-13 | Closed | Verified by QA

## Sheet2
Logical
User Interface
Maintainability
Standards
Others