## Defect Tracker Update Blank Dat
Sl No | Submitted By | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Status | Remarks
1 | Anugraha | Agent repeating research steps in shared memory | Sprint 3 | Anugraha | Logical | Added is_duplicate helper function | Closed | Tested successfully
2 | Anugraha | uvicorn command not found; app fails to start | Sprint 4 | Anugraha | Environment | Installed uvicorn & updated requirements.txt | Closed | Verified in terminal
3 | Anugraha | UI results not rendering after "Run" click | Sprint 4 | Anugraha | UI | Fixed frontend fetch & rendering logic | Closed | Verified by user
4 | Anugraha | Response time too high for multi-agent tasks | Sprint 4 | Anugraha | Performance | Optimized prompt handling | Closed | Needs more tuning